Risk Register

Clara

Document 12 of 13: Risk Register

Version 0.2 - Draft for Review

Author: Rafif Muhammad Ransi Anargya

Date: 21 September 2026

# 1. Purpose

This document tracks the specific risks identified during planning, so that each has a named owner and a review date rather than existing only as a paragraph in a strategy document. It replaces the register drafted for the withdrawn StellarStream direction; risks specific to that product have been removed rather than carried over for appearance.

| ID | Risk | Likelihood | Impact | Mitigation | Owner | Next review |
| --- | --- | --- | --- | --- | --- | --- |
| R1 | The upstream x402 discovery conventions change during the grant period, invalidating catalogue schema or endpoint design. | High | Medium | Treated as expected rather than exceptional: the request for proposals requires tracking it. Isolate specification-dependent code behind an adapter; the Change Management Policy carries an explicit upstream-tracking clause. | Rafif | Monthly |
| R2 | An adjacent team ships a competing Stellar facilitator or discovery layer first. | Medium | High | Confirm current scope of publicly active x402 work, specifically the TKCollective x402 research repository, before submission; prefer partnership over collision if scopes overlap. | Rafif | Before submission, then monthly |
| R3 | An AGPL-licensed component enters the dependency tree transitively and disqualifies the grant. | Medium | High | Automated licence scanning of the full transitive tree in continuous integration, failing the build on any match; treated as a release blocker per the Test Plan and QA Strategy. | Rafif | Every release |
| R4 | Search relevance is graded below the acceptance bar, jeopardising the highest-value milestone. | Medium | High | Held-out query set and precision-at-five measurement from the start of Phase 1, per the Test Plan and QA Strategy, so quality is known early rather than discovered at review. | Rafif | At each Phase 1 checkpoint |
| R5 | The third-party audit returns findings that delay the mainnet production tag. | Medium | Medium | Engage the Audit Bank early rather than at the end of Phase 2; run the validation negative-test suite continuously so that the audit encounters few first-time findings. | Rafif | At Phase 2 entry |
| R6 | A validation defect accepts an invalid payment, causing a seller to lose money and Clara to lose trust. | Low | High | Exact-match validation on every field with no tolerance bands; negative-test-first development of the validator; simulation before submission; independent audit of this specific path. | Rafif | Every release |
| R7 | Regulatory reclassification: operating a non-custodial facilitator is treated as a regulated activity in a target jurisdiction. | Low | High | Obtain qualified legal analysis before any pubnet launch carrying third-party volume, per the Data Privacy and Compliance Note; the non-custodial architecture is a deliberate mitigation but not a legal conclusion. | Rafif | Before pubnet launch |
| R8 | Catalogue abuse at scale: spam, impersonation, or listings hostile to consuming agents overwhelm integrity checks. | Medium | Medium | Quarantine-by-default for failed checks, per-key attribution and bulk quarantine, periodic revalidation of live listings, and the takedown procedure in the Runbook and Operations Manual. | Rafif | Quarterly |
| R9 | Agent-payment demand on Stellar does not materialise at a scale that sustains the service commercially. | Medium | High | Track catalogue size, settlement volume, and unique paying agents quarterly against the Business Case assumptions; the grant funds the build, so commercial viability is tested before, not after, operating costs scale. | Rafif | Quarterly |
| R10 | Grant funding is delayed, reduced, or not renewed beyond the initial tranches. | Low | High | Sequence spending to each tranche milestone rather than the full award; treat Phase 2 as conditional on tranche release. | Rafif | At each tranche milestone |
| R11 | Key-person dependency: the project currently has a single primary contributor. | High | High | Document architecture and operations thoroughly, as in this document set, specifically so the project is not solely dependent on one person's undocumented knowledge. | Rafif | Quarterly |

Risks carried forward from the StellarStream register with their substance changed: the former R1, concerning SDF extending its own tooling to remove the need for the product, now appears as R2 in the form it actually takes for this product, which is a competing facilitator rather than a first-party streaming feature. The former R3, concerning operational capacity for always-on infrastructure, is retained in substance through the phase sequencing described in the Product Requirements Document, but is no longer listed as a standalone risk because Clara's settlement path is stateless request-response rather than a continuously ingesting process, which materially reduces it.